## Old Plan
|  |  | Week ending | 2016-05-13 | 2016-05-20 | 2016-05-27 | 2016-06-03 | 2016-06-10 | 2016-06-17 | 2016-06-24 | 2016-07-01 | 2016-07-08 | 2016-07-15 | 2016-07-22
| Component | Activity | Resource
Preriquisites |  | Create Nest account and Nest Simulator for CO | bar: 2016-05-13
Create Nest developer account and register a product | bar: 2016-05-13
Digital | Landing Page | Design the landing page and authorization module | bar: 2016-05-20
Develop landing page (with Find my Policy integration) | bar: 2016-05-27 to 2016-06-03
| Authorization Module | Develop authorization module (includes sending authorization data to EADS API) | bar: 2016-06-10 to 2016-06-17
Test the Digital solution through simulators in Nest accounts (for 10-15 devices encompassing various structures) | bar: 2016-06-24
EADS |  | Write test cases to test application based on product requirements and features (consider various device structures) | QA | bar: 2016-05-20
| Data Model | Design data model and develop data structures to store authorization data and Nest Device data based on UBI/Telematics data structures | API Developer | bar: 2016-05-13
| Authorization Retention API | Develop API for digital to send authorization data | API Developer | bar: 2016-05-20 to 2016-05-27
| Access Token API Call | Develop component to exchange auth code for access token | API Developer | bar: 2016-05-27 to 2016-06-03
| Real-Time/Batch Connection | Develop POC to test real-time connection using firebase libraries (use pin based authentication for test) and batch connection using REST to evaluate the best architecture | API Developer | bar: 2016-06-03
|  | Develop real-time/batch connection based on POC | API Developer | bar: 2016-06-10 to 2016-06-17
|  | Test the EADS solution through simulators in Nest accounts (for 10-15 devices encompassing various structures) | API Developer | bar: 2016-06-24
Digital and EADS |  | Integration Testing | bar: 2016-07-01
Deploy to Prod | bar: 2016-07-08
User Acceptance Testing | bar: 2016-07-08 to 2016-07-15
Nest Product Review | bar: 2016-07-15 to 2016-07-22